## Sheet1
Sl.No | Work Priority
1 | Login Page Loader
2 | Recipe Pdf Upload
3 | Recipe- What You Need ?
4 | Swag Module (List , Add, Edit , Delete)
5 | Menu Module (List , Add, Edit , Delete)
6 | Search Box for All Module (Recipe,users,Ingredients,Portions)
7 | In Ingredients and Portions Instead of Delete Publish or UnPublish
8 | Site Setting Page
9 | Email Setting Page
10 | Admin Setting Page & Change Password
11 | Forgot Password Module
12 | Review Management Module
13 | Sales Order Management
14 | Coupon Code Management
15 | Subscription Notification
16 | News Letter User Management

## 06-09-2017
Pending Work | Status
In Menu While Clicking Next if there is no Menu Added Show No Recipes Found. | Pending
While Clicking Edit in Swag it is showing "Edit Recipe " in pop up. Instead need to show editing Swag | Pending
In Swag Add Price and Quantity is Mandatory | Pending
In Reviews Listing instead of "Reviewer" change to "Nickname", Rating Percentage in Stars, and status in text Enable or Disable, Add New Column "Type"=> Guest/Customer. New Column "Email". | Pending
In Subscription List Change Status 1=> Enable | Pending
In Ingredient Remove Delete button instead Show Status enable/disable | Pending
In Portions Remove Delete button instead Show Status enable/disable | Pending
Forgot Password | Pending
By Default if it is less than 10 pagination should not come ==>check portion/ingredient module | Pending
User Module : While Clicking Add Pop up showing "Edit Customer" | Pending
While clicking submit button in Edit Profile Loader is not Showing | Pending