## Sheet1
Sl.No | Work Priority
1 | Login Page Loader
2 | Recipe Pdf Upload
3 | Recipe- What You Need ?
4 | Swag Module (List , Add, Edit , Delete)
5 | Menu Module (List , Add, Edit , Delete)
6 | Search Box for All Module (Recipe,users,Ingredients,Portions)
7 | In Ingredients and Portions Instead of Delete Publish or UnPublish
8 | Site Setting Page
9 | Email Setting Page
10 | Admin Setting Page & Change Password
11 | Forgot Password Module
12 | Review Management Module
13 | Sales Order Management
14 | Coupon Code Management
15 | Subscription Notification
16 | News Letter User Management

## 06-09-2017
Pending Work | Status
In Menu While Clicking Next if there is no Menu Added Show No Recipes Found. | Completed
While Clicking Edit in Swag it is showing "Edit Recipe " in pop up. Instead need to show editing Swag | Completed | Initially while editing it is showing add then it is changing to Edit. This must be changed need to show only edit
In Swag Add Price and Quantity is Mandatory | Completed
In Reviews Listing instead of "Reviewer" change to "Nickname", Rating Percentage in Stars, and status in text Enable or Disable, Add New Column "Type"=> Guest/Customer. New Column "Email". | Completed
In Subscription List Change Status 1=> Enable | Completed
In Ingredient Remove Delete button instead Show Status enable/disable | Completed
In Portions Remove Delete button instead Show Status enable/disable | Completed
Forgot Password | Completed
By Default if it is less than 10 pagination should not come ==>check portion/ingredient module | Completed
User Module : While Clicking Add Pop up showing "Edit Customer" | Pending | Not Fixed now it is showing both
While clicking submit button in Edit Profile Loader is not Showing | Completed
While clicking pagination in ingredient and portion load need to come | Pending
While Clicking next and previous in Menu Loader required | Pending
while clicking add recipe showing error | Pending

## Admin-oct-02-2017
Bugs | Status
Admin Recipe
Recipe After Adding Should Redirect to Recipe Listing Page | Pending
Recipe Pdf Is not uploading | Pending
while Edit Recipe The images are removed | Pending
Last Added Recipe Need To come First | Pending
Admin Swag
Swag Listing service url is wrong below is the service pls check for the correct parameters http://freshbox.white-space-studio-dev.com/webservices/swag/list.php | Pending
Swag Add also not storing the right parameters Please check the Below service url http://freshbox.white-space-studio-dev.com/webservices/swag/add.php | Pending
While Editing Swag Images Disappear | Pending
Last Added Swag Should need to display first | Pending
Users Admin
While Clicking Add in Pop up it is showing Add Customer as well as Edit Customer both | Pending
Last Added Users Should come first | Pending
While Clicking Pagination page loader need to occurs | Pending
Reviews Admin
Remove Add Button in Review Listing | Pending
Subscribers
Remove Add Button from the Subscriber list | Pending
Front End
While visiting recipe Detail page and returning back to listing the loading content is not disappearing | Pending
Footer Need to be Aligned Properly | Pending
Swag Link is Removed please add it in the footer | Pending