## Sheet1
Bug # | User | Section | Description
1 |  | Newsletter | Once registration is complete, it should go to a separate thank you page with a better description.
2 |  | Registration | /cart/checkout. The password is visible. Also, remove the top box if they are just signing up without registering.
3 |  | Meal Preference | If you are a newly registered user, it is not possible to choose meal preference and checkout. Bug here.
4 |  | Checkout | When on the steps, they should be highlighted in Green and also on clicking the steps, you should be able to go to the steps.
5 |  | Checkout | Adding an address on the checkout page does not add it on the addresses page in the backend.
6 |  | Addresses | Changing default addresses and clicking on the default should automatically save rather than clicking on Submit.
7 |  | Checkout | Use this as my Billing Info checkbox does not work, and neither does adding a new address work.
8 |  | Checkout | Clicking on Edit beside the billing and shipping addresses do not work. Both of the addresses seems to change both the times.
9 |  | Checkout | For some reason, there is no meal preferences circles when checking out.
10 |  | Checkout | Step 4, make sure that there is a default card. It is not obvious.
11 |  | Checkout | The comments are not showing up on checkout.
12 |  | Checkout | There is an added $50 in the checkout, what is it for? It does not show anything beside it.
13 |  | Checkout | Also, we should be able to click on step 5 if it is already filled.
14 |  | Checkout | There is a shipping and handling charge, where is this being calculated? This doesn't seem to change.
15 | ADMIN | Orders | In the invoice, there is a new amount of 50 + 15 adding up to the total without showing. Addition of preferences is not showing.
16 | ADMIN | Orders | In the orders, currently there is no way for the admin to know what preferences the user has put.
17 | User | Orders | There is a button CANCEL on the top, what happens on Clicking it? Do you get a refund?
18 |  |  | There should be a page "Weekly Orders" with all preferences so that all the weekly orders are shown.
19 |  | Account/profile | Mobile number is not being saved.
20 |  | general | The green message box on success is at the top and is not visiblle to the users.
21 |  | Change Password | When changing password, the error message should show inside the lightbox and also the message "Server Error" is not enough.
22 |  | Change Password | The password notification should also be shown here.
23 |  | Login and Security | Remove Two Step Verification
24 |  | Add Credit Card | Show date and CVV format
25 |  | Add Credit Card | Also does not show until refresh. Make it Ajaxed.
26 |  | Cards | Make Delete look like a button
27 |  | Cards | There should be a default card.
28 |  | Addresses | Clicking on Default make the default disappear.
29 |  | Addresses | For some reason, it was possible to delete the default address.
30 |  | Addresses | The default address should be in blue, there is a but in the default.
31 |  | My Recipes | Duplicating a cookbook title freezes the screen
32 |  | general | Once logged in add to cookbook should be there.
33 |  | Menu | Add to favorites isn't working until refresh. Wrong favorites are being toggled on the front end.
34 |  | Menu | Take a look at the January 2 menu, something is wrong.
35 |  | Dashboard | Unsubscribe button, what does it do? It is supposed to remove you from Subscription.